## Australian Government Productivity Commission logoWorkplace Culture Reform (WCR) program

## Action plan and status of implementing each recommendation

**Updated:** 31 October 2024

## WCR program – action plan

| **Key activities** | **Development and delivery period** | **Month completed or scheduled to finalise** | **Status** |
| --- | --- | --- | --- |
| 1. **Establish WCR program** Action Plan, Engagement Plan and Reporting Framework endorsed to roll out with continual review, streamlining and adjustments as required, with consideration to appropriate scheduling, risk management, ongoing staff consultation and alignment with broader organisational change management activities. Establish monthly updates to all staff on progress and develop a Culture and Wellbeing Hub for staff communications. | October to February | February | **Completed** |
| 1. **Statement of Intent established in response to Government’s Statement of Expectations** Include Commission’s commitment to implementing all recommendation of the Intersection Review, and plans to strengthen the Commission’s culture and governance arrangements. | November to February | February | **Completed** |
| 1. **Increase counselling support – including through HCO and EAP reviews** Provide role review and fill vacant roles via an EOI, provide ongoing training and establish quarterly HCO meetings. Include updates to HCO role/procedures in Workplace Behaviour Policy and Procedures. Provide EAP accessibility refresh, seminars and improved promotion of services and toolkits. Provide Mental Health First Aid Training to interested staff via an EOI process. | November to February | February | **Completed** |
| 1. **Review/streamline WCR Action Plan and finalise policy review schedule and WCR risk management plan (risk register)** Align policy schedule and organisational change projects in progress. identify risk management priorities and approach to inform and establish a risk register. Conduct a review of the policy schedule to ensure that relevant policies are updated as per review recommendations and implementation timelines. Prioritisation of key policies including the Workplace Behaviour Policy, WHS policy and Performance management policies for SES and Non-SES employees as well as strategies – Workforce Strategy and Inclusion and Diversity Strategy. | February to March | March | **Completed** |
| 1. **Workplace culture engagement plan**  Develop an engagement plan to enable staff interaction and visibility of progress during implementation and to improve connections between aligned efforts across the Commission. Launch via new Culture and Wellbeing Hub, with revisions over time as required. | December to February | March | **Completed** |
| 1. **Workplace culture reporting framework** Development of a workplace culture reporting framework, outlining all relevant reporting streams inclusive of dates and forums. Report on workforce analytics, staff wellbeing and behaviours, workforce engagement, capability and development. Launch via Culture and Wellbeing Hub, and revise Framework over time as required. | December to March | March | **Completed** |
| 1. **Bystander intervention training** (all staff and leaders)Workshops offered to all staff, including SES and Commissioners. | November to March | March | **Completed** |
| 1. **Procurement to outsource breaches of the code** Two providers (fee for service) identified and contracted to use when/if required. | February to April | April | **Completed** |
| 1. **PC Values (organisational / behavioural attributes)**   Co-creation of new organisational values with all staff (PC Values: Inclusive, Collaborative, Influential, Respectful, Supportive). | March to May | May | **Completed** |
| 1. **Unconscious bias training** (all staff and leaders)Provide workshops to all staff, including SES and Commissioners. | April to June | June | **Completed** |
| 1. **Inclusion and Diversity Strategy 2024–28**   Co-creation with staff via focus groups, drafting and gathering extensive feedback to finalise and launch strategy with all PC staff. | November to July | July | **Completed** |
| 1. **Speak up campaign** – launch / announcement of various activities   Head of Office update/s; develop new resources including launch of Speak up hub; seminars; mandatory compliance training modules for all staff; managers toolkit updates, staff surveys, trauma informed practice training for HR team and establishing a Commissioners Charter. | April to August | April to August | **Completed** |
| * **Trauma informed response training for HR team** | May | May | **Completed** |
| * **Building respectful working relationships**  TELUS Health lunch and learn seminar. | May | May | **Completed** |
| * **Open staff survey: 2024 APS Employee Census**   Survey feedback to inform workforce indicators relating to wellbeing, behaviours and culture. | May to June | June | **Completed** |
| * **Emotional Intelligence** TELUS Health lunch and learn seminar. | June | June | **Completed** |
| * **Mandatory compliance training program (e-learning)** APS and Comcare modules on key learning topics including WHS, Inclusion and Diversity and Integrity in the APS. | September to June | June | **Completed** |
| * **Managing difficult conversations**   TELUS Health lunch and learn seminar. | July | July | **Completed** |
| * **Manager’s Toolkit review & update**   Revamp existing resources for currency and to provide greater clarity. Added new resources: psychological safety, promoting a positive workplace culture, supervisor tip-sheets informed by EAP resources. | July | July | **Completed** |
| * **Commissioners Charter**   Chair and Commissioners work together to develop and sign off Charter and launch with all staff. | March to July | August | **Completed** |
| * **Open staff survey:** **2024 PC Culture Survey (1/2)** Co-design and administer culture survey through an external third party, and use results to establish a baseline score/assessment of culture. | July to August | August | **Completed** |
| * **Release survey results**: 2024 APS Census and 2024 PC Culture Survey (1/2)  Management and group/team discussions to discuss results, SES sponsor allocated for action planning process. | August | August | **Completed** |
| 1. **External anonymous complaints service**  Procure service and provide training to relevant key personnel (reviewers/delegates). Launch with all staff, apply intranet updates. | April to August | August | **Completed** |
| 1. **Project management capability uplift** (Terrace Services)   New project management methodologies adopted by teams, agency-wide adoption of Asana commenced, templates and processes being embedded. Project Management Oversight Committee (PMOC) established. Uplift informed by the Independent Review and staff feedback received from pulse surveys and Census results discussions about project management practices, including impacts on behaviour and wellbeing. | April to August | August | **Completed** |
| 1. **Succession plan for complex case management**   Review of HR team structure and associated recruitment activities to backfill vacancies at the EL2 and EL1 levels, and sufficient coverage and expertise for complex case management. | March to August | August | **Completed** |
| 1. **Include workforce/culture focus in Corporate Plan**   ‘Investing in our organisational culture and capability’ section added to Corporate Plan 2024–2028, including achievements following the release of the Intersection Review. | July to August | August | **Completed** |
| 1. **Establish the Workplace Improvement and Culture Committee (WICC) via an EOI process**   Purpose: To bring a diverse membership of staff together to collaborate and contribute to the delivery of actions under the Inclusion and Diversity Strategy and other workplace initiatives to improve the workplace and actively foster a safe, inclusive and productive culture. | May to September | September | **Completed** |
| 1. **Quarterly culture reporting commences**   Provide quarterly culture reports to leaders, Committees and all staff, in accordance with the workplace culture reporting framework. A culture reporting page launched for all staff to access updates. | April to September | September | **Completed** |
| 1. **Work Health and Safety (WHS) Policy and WHS management system update**   Updated for best **practice** and currency with WHS and related legislation, including psychosocial safety and positive duty requirements. | April to September | October | **Completed** |
| 1. **Report on progress of implementing the Independent Review recommendations after 12 months** Provide an update to the Treasurer on the progress of implementing the Intersection Review recommendations and share the action plan. Share the update to all staff and publish the update for transparency. | October | October | **Completed** |
| 1. **PC Culture Survey (2/2)** The Survey is scheduled for late November 2024 and will continue to run annually in November (six months from the APS Census). | October to November | November | **In progress** |
| 1. **PC Workforce Strategy / Workforce Planning Project** (TMS Consulting)Development of the PC Workforce Strategy is underway, following extensive review of the PC’s workforce planning and capability needs, including a skills survey conducted with all staff. Strategy to be released for Consultation with all staff in early 2025 to inform the final Workforce Strategy for endorsement by the Management Committee. | Late 2023 to early 2025 | Q3 2024-25 | **In progress** |
| 1. **Consultation and action planning on survey results** Develop the 2024 APS Census Action Plan for public release in November 2024, with consideration to 2024 Census results and PC Culture Survey (1/2) results, and progress against the 2023 Census Action Plan. | August to November | Q2 2024-25 | **In progress** |
| 1. **Operational plan development (for I&D strategy implementation) via co-design process** Engage consultant with expertise in Inclusion and Diversity and working with diverse groups (completed).   Meetings with WICC and key staff to plan and schedule activities, and develop operational plan (in progress).  Management Committee endorses operational plan, followed by launch with all staff and oversight by the WICC (TBC). | July to November | Q2 2024-25 | **In progress** |
| 1. **Review governance arrangements for workplace culture and broader organisational transformation**  * Review organisation-wide governance arrangements including sub-Committees of the Management Committee, reporting arrangements, Committee functions, etc. and review and develop terms of reference as needed – WICC, PMOC, etc. (completed). * Improve role clarity/purpose for Committees and staff networks through review/development of terms of reference (as required), I&D Operational Plan, intranet page updates (including Communities pages) and a visual placemat for Commission wide governance arrangements and authorising environment (in progress). | April to November | Q2 2024-25 | **In progress** |
| 1. **Learning and development bundle**   a. Leadership sponsorship opportunities (SES and EL2) and cohort development days provided. A review of HR delegations to provide additional delegation at the EL2 and SES Band 1 levels, and prepare a forward plan for agency-wide training (L&D calendar) for 2024-25 (completed).  b. Training sessions for all staff (and leaders workshops as required) in the areas of bystander intervention, unconscious bias, cultural capability, giving and receiving feedback, emotional intelligence, building respectful workplace relationships, having difficult conversations. Trauma informed victim-centred response workshop for HR practitioners (completed).  c. Training workshops and internal information sessions for all staff to promote and embed the revised workplace behaviour policy and procedures, including custom briefings for leaders, HR practitioners and HCOs as required. Training session for SES and Commissioners on bystander intervention, and training sessions for leaders (Commissioners, SES and EL2s) on providing a trauma informed, victim-centred approach. Update Managers Toolkit and Induction resources for managers to include relevant guidance materials, as available, following delivery of these training programs to ensure consistent leadership practices (in progress). | Late 2023 to early 2025 | Q3 2024-25 | **In progress** |
| 1. **Workplace behaviour policy and procedures (WBPP) update and supporting procedures roll out** a. Undertake staff consultation process to inform WBPP update (completed). b. Obtain Management Committee endorsement of final WBPP update (completed). c. Release updated policy with all staff; apply intranet updates for alignment with WBPP (pending). d. Promote WBPP in practice through release of subsequent training and information sessions (pending). | April to November | Q2 2024-25 | **In progress** |
| 1. **SES Performance and Leadership Framework** Update the SES Performance management policy and procedures to comply with mandatory [APS-wide SES Performance Leadership Framework](https://www.apsc.gov.au/sites/default/files/2023-08/SES%20performance%20leadership%20framework.pdf) by 1 January 2025, and incorporate relevant leadership performance agreement practices as outlined in the Independent Review (in progress). | August to December | Q2 2024-25 | **In progress** |
| 1. **Recruitment practices guidelines review / update**   a. All leadership positions advertised include behavioural and leadership capability attributes from the capability framework, and this is assessed during application and interview process (active, current process).  b. Review/update HR delegations – with additional delegations provided to EL2s and SES Band 1s (completed).  c. Review/enhance current process for assessing leadership capabilities/skills during recruitment processes following Workforce Strategy and Capability Framework update, with consideration to Independent Review recommendations relating to leadership capabilities, recruitment and performance procedures (pending).  d. Review selection reports/templates and scribe procedures; investigate e-recruitment system options and investigate the need to develop an Employee Value Proposition (EVP) and/or update the PC’s Careers pages (pending). | May to December | Q3 2024-25 | **In progress** |
| 1. **Non-SES Performance and development policy and capability framework** (review/update) Following the updated SES Performance and Leadership Framework and the new Workforce Strategy, update the performance and development policy and procedures for non-SES level employees, including ratings and performance agreement processes – including to effectively capture and assess leadership performance and providing corporate contributions. Review capability framework to align with new groups and streams and required capabilities (leadership behaviours, technical skills, etc.) to be identified in the Workforce Strategy, Statement of expectations and Independent Review of Workplace Culture. | August to December | Q4 2024-25 | **Planning in progress** |
| 1. **Workplace behaviour training** (all staff)*S*chedule and deliver workplace behaviour policy training workshops and information sessions to all staff, including any customised sessions required for HR personnel, HCOs, managers and leaders. These sessions may be delivered in-house and/or with assistance of an external provider. | May/June | Q3 / Q4 2024-25 | **Planning in progress** |
| 1. **Bystander intervention training** (additional session for Commissioners and SES) With assistance of an external provider, deliver bystander intervention training workshops to leaders, with all SES and Commissioners to attend if not already completed. | June | Q3 2024-25 | **Planning in progress** |
| 1. **Trauma informed response training for leaders** (Commissioners, SES and EL2s)   With assistance of an external provider, deliver trauma informed, victim-centred response training to leaders – with Commissioners and SES to take place first, followed by EL2s. | June | Q3 2024-25 | **Planning in progress** |

## Status of implementing each recommendation (in accordance with the action plan)

| **Recommendations** | **Action plan #** | **Implementation Status** |
| --- | --- | --- |
| 1. The Chair confirms the Commission’s commitment to providing a safe, respectful and inclusive workplace. The Chair, Commissioners and senior leaders develop a plan for the implementation of these recommendations. | 1, 2, 4, 5, 6, 16, 20 | **Completed** |
| 1. All leaders actively and consistently message expectations of workplace behaviour and corresponding consequences for breaches. | 5, 7, 9, 11, 12, 26a,b,c, 27a,b,c,d 28, 29, 30, 31, 32, 33 | **In progress** |
| 1. All leaders understand their role in setting and reinforcing a positive workplace culture and are held accountable for this through the inclusion of behavioural indicators in performance agreements. | 5, 6, 7, 9, 11, 12, 19 26a,b,c 27a,b,c,d, 28, 30, 31, 32, 33 | **In progress** |
| 1. All leaders and managers are provided with leadership and people management training appropriate to their level and access to ongoing leadership development to ensure leadership practice is contemporary. | 7, 10, 12, 19, 26a,b,c, 27a,b,c,d 31, 32, 33 | **In progress** |
| 1. All leaders be trained in trauma-informed, victim-centred approach so they can respond to disclosures of inappropriate behaviour in a manner that ensures complainants are supported and no further harm is caused. | 33 | **Planning in progress** |
| 1. Development of the updated Diversity and Inclusion Strategy be prioritised with a focus on creating a safe, respectful and inclusive workplace and the recruitment and retention of employees with diverse skills, experience and background. | 7, 17, 24 | **Completed** |
| 1. Actions to address the risks identified in this report, and any others that may be subsequently identified, are documented including appropriate mitigations and reported to Commission Meetings on a quarterly basis. | 4, 6 | **Completed** |
| 1. Recruitment for leadership positions prioritises people and leadership management skills and experience in addition to technical knowledge and skill. | 22, 29a,b,c,d | **In progress** |
| 1. Project delivery model and consequent workload issues be reviewed to understand the impact and pressures on Commission staff insofar as these relate to instances of inappropriate workplace behaviour. | 14, 25 | **Completed** |
| 1. The Chair, Commissioners and senior leaders ensure respectful challenge and contestability processes with inappropriate and disrespectful behaviours being actively called out and addressed. | 6, 7, 12, 14, 26a,b,c, 27a,b,c,d 31, 32, 33 | **In progress** |
| 1. The Workplace Behaviour Policy be updated to include a section to clearly define what constitutes the workplace, and the responsibilities and expectations of staff socialising outside of work hours and off-site. In addition, the following recommendations are made to strengthen the policy and ensure alignment with leading practice: 2. That sexual harassment be a distinct section of the policy, and as such separated out from sex-based harassment within the discrimination section of the policy. This new section should also include a comprehensive list of sexual harassment behaviours. Additionally, given a number of the reported incidents of inappropriate workplace behaviour were undertaken with or through technology, there should be a clear reference to the use of technology in perpetrating sexual harassment and other inappropriate workplace behaviours. 3. The discrimination section be amended to include definitions and examples of indirect and direct forms of discrimination, and align with efforts to address these proactively. | 27a,b | **Completed** |
| 1. All HR personnel be trained in trauma-informed, victim-centred response so that no further harm is caused to complainants. | 12 | **Completed** |
| 1. The role of the Harassment Contact Officer (HCO) role is clarified and communicated to all Commission staff including ensuring there is:    * a clear role description    * an organisation-wide, transparent Expression of Interest (EOI) process is used to advertise the HCO positions    * a skills-based approach is used to select the HCOs including assessment of suitability    * ongoing professional development and support is provided to those appointed, and    * consideration of a set-term for HCOs to avoid burn-out. | 3, 12 | **Completed** |
| 1. Increased counselling support is available for staff who have experienced significant psychological impacts from inappropriate workplace behaviour. | 3, 12 | **Completed** |
| 1. Complainants are appropriately and sensitively supported through a complaint process. | 6, 8, 12, 13, 19, 26a,b,c 27a,b,c,d, 31, 33 | **In progress** |
| 1. The Commission consider the adoption of an external anonymous complaint handling service. | 13 | **Completed** |
| 1. Complainants are kept informed of the process and its progress at regular intervals. | 6, 8, 12, 13, 15, 19, 26a,b,c 27a,b,c,d, 31, 33 | **In progress** |
| 1. Complainants are informed of the outcomes of their complaint. |
| 1. Informal complaints/reports are dealt with in real time and managers are responsible for informing HR (de-identified if so requested) so that they can be added to the Central Workplace Behaviour Register. |
| 1. Where complaints are not found to have breached the APS Code of Conduct but are still found to be incidents of inappropriate behaviour, that proportionate action is taken which may include for example, group/team/individual level training and discussion about behavioural expectations. |
| 1. In addition to the APS Census, the Commission (through an independent third party) undertake a workplace culture survey to establish a baseline against which future progress can be measured, that specifically looking at the nature, impact and prevalence of inappropriate workplace behaviour, and any barriers to reporting. | 12, 18, 23 | **Completed** |
| 1. That the above survey data as well as de-identified data on complaints and actions taken be shared with the workforce to build confidence and trust in reporting mechanisms. (Given the small size of the workforce this may be once a year to ensure confidentiality.) | 6, 12, 18 | **Completed** |
| 1. That reports of inappropriate behaviour (de-identified) are shared with the Management Committee as the most senior governance mechanism on a regular basis (e.g. a standing item each quarter) in line with the risk management process outlined in Rec. 7. | 4, 6, 18 | **Completed** |